ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	1

1.1.	Partner country	1

1.2.	Contracting authority	1

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	Specific objective(s)	2

2.3.	Expected outputs to be achieved by the contractor	2

3.	ASSUMPTIONS & RISKS	2

3.1.	Assumptions underlying the project	2

3.2.	Risks	2

4.	SCOPE OF THE WORK	2

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation	4

6.	REQUIREMENTS	4

6.1.	Personnel	4

6.2.	Office accommodation	8

6.3.	Facilities to be provided by the contractor	8

6.4.	Equipment	8

6.5.	Incidental expenditure	8

6.6.	Lump sums	8

7.	REPORTS	8

7.1.	Reporting requirements	8

7.2.	Submission & approval of reports	9

8.	MONITORING AND EVALUATION	9

8.1.	Definition of indicators	9

8.2.	Special requirements	9

# BACKGROUND INFORMATION

## Partner country

Republic of Armenia

## Contracting authority

European Union Mission in Armenia (EUMA).

## Country background

The strategic objective of EUMA Armenia is to contribute to a reduction in the number of incidents in conflict-affected and border areas of Armenia, to reduce the level of risk to the population living in these areas, and to build confidence between the populations and authorities of both Armenia and Azerbaijan.

## Current situation in the sector

N/A

## Related programs and other donor activities

N/A

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is:

To provide the mission with vehicle tracking services as outlined in this ToR. Therefore, a service provider needs to be identified.

## Specific objective(s)

The specific objective (Outcome) of this contract is as follows:

- Provide the mission with vehicle tracking services

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

- Output 1: Identify a service provider, to Outcome 1: Provide the mission with vehicle tracking services

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The funding of these services must remain within the limits of the budget allocated to EUMA for the implementation of this project.

## Risks

If a VTS is not implemented, there is a risk that the mission is unaware of an MM’s current position when travelling or on patrol should they be involved in traffic accidents or whose vehicle faces technical difficulties and/or are exposed to other road and country related risks such as severe weather conditions. The likelihood of these risks is considered high. The impact of the risk may vary from low (MM has to wait until a broken-down vehicle can be recovered) to very high (a MM involved in a severe traffic accident whose location is unknown and who is hurt by the accident and whose injuries are life-threatening. The implementation of a VTS will significantly reduce such risks both in terms of likelihood and impact.

# SCOPE OF THE WORK

## General

### Project description

To provide a Vehicle Tracking System for the whole EUMA Fleet for an initial period of 24 months, renewable for 12+12 months.

Carry out daily management and maintenance activities as may be required to ensure the smooth functioning of the Vehicle Tracking System.

Maintain a secure connection for data collection through existing commercially operated GPRS or 3/4/5G and/or satellite networks within the Mission area and provide secure web-based access to such data for monitoring and reporting purposes. The requirements are outlined in full in Annex 1 - Requirements on page 10.

### Geographical area to be covered

The Vehicle Tracking System service must cover the entire territory of Armenia, Georgia and Turkey. Upon request, neighbouring countries and Europe need to be covered. This feature (roaming) is activated/deactivated by authorised users primarily via a dedicated platform and, as a back-up, via request emails to the VTS contractor.

### Target groups

N/A

## Specific work

- Facilitate access to databases by authorised EUMA personnel to data (i.e. vehicle/driver activity data) at any time.

- Installing and/or upgrading VTS hardware, updating equipment firmware/software throughout the EUMA vehicle fleet.

- Day-to-day management and maintenance of the system.

- The Contractor shall establish and maintain at EUMA a buffer stock of five (5) complete sets of hardware and data transmission equipment for rapid reinstallation in/between EUMA vehicles.

  - The contractor will send to and maintain a buffer stock at EUMA site of the accessories.

  - The implementation of the buffer stock will be managed jointly by the Contractor, the Contracting Authority and any other authorized third-party named by the Contracting Authority.

  - The duration of the buffer stock corresponds to the contract duration.

  - The Contractor is in charge of shipping the accessories to the Contracting Authority and will bear the costs for DAP shipment. The Contracting Authority is in charge of shipping the accessories back to the Contractor at the end of the contract and will bear the costs for DAP shipment.

  - In the event of non-return of the equipment and/or observed damages, the compensation costs to be borne by the Contracting Authority will be the value of the respective accessory as described by the Contractor in the Budget Breakdown.

- On an as-needed basis - uninstallation of hardware from old vehicles and its installation in new vehicles joining the fleet - to be coordinated by the EUMA Transport Unit.

- On an as-needed basis - removal of faulty hardware (or its malfunctioning elements) from vehicles and its reinstallation - to be coordinated by the EUMA Transport Unit.

- On an as-needed basis - replacement of already used/malfunctioning equipment; to be sent to the address of the service supplier, as well as RFID readers (or equivalent), relays, GPS antennas, batteries or any other type of equipment leased to the contractor.

- The Service Provider, following all provisions of these Conditions, should describe its management approach as regards the performance of the services. In particular, the management methodology proposed by the Service Provider must include and demonstrate how business continuity of the system will be ensured.

## Project management

### Responsible body

The Transport unit of EUMA will be responsible for monitoring and receiving the project. Communication between the parties should be done by email, e.g. every time the Contracting Authority wishes to un/install a VTS on a vehicle or carry out maintenance on the hard/software, it will accordingly inform the Service Provider by means of purchase orders or email.

Payment will be made by the Mission’s Finance Department.

### Management structure

The Head of Transport Unit or delegates.

### Facilities to be provided by the contracting authority and/or other parties

N/A

# LOGISTICS AND TIMING

## Location

The contract will be implemented:

On the place of performance with the following locations: The contract will be implemented in Yeghegnadzor, Armenia and the place of performance will be in Armenia, Georgia & Turkey.

## Start date & period of implementation

The intended start date is 1 January 2027 and the period of implementation of the contract will be 24 (extendable 12+12) months from this date. Please see point 3 of the main conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Personnel

Note that civil servants and other staff of the public administration, of the partner country or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

The selection procedures used by the contractor to select the experts must be transparent, must guarantee the absence of professional conflicting interests and the absence of any discrimination based on former or current nationality, gender, place of residence, or any other ground. The findings of the selection panel must be recorded.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Key experts

Key experts have a crucial role in implementing the contract. These terms of reference contain the minimum requirements for the key experts.

Although minimum requirements for the experts are not selection criteria but award criteria meant to evaluate the technical quality of the offer, the compliance with these requirements is assessed on a YES/NO basis. If an expert does not meet the minimum requirements, the expert must be rejected on the basis of non-compliance. This means that the entire tender is rejected and shall not be evaluated further.

During the evaluation, higher scores will be awarded to the “Expert’s Profile” that demonstrates, in addition to the minimum requirements, strengths in relation to the objectives, expected outputs, and scope of work. The award criteria may include additional desirable qualifications, skills and professional experience. These additional desirable criteria, will provide guidance on the elements that will be considered a strength and will receive higher scores.

The “Key Expert’s profile” (Annex IV) shall be submitted by the tenderer for the following key experts:

Compliance with these requirements shall be proven through the provision of educational certificates and work certificates/employer statements or work/consultancy contracts.

Key expert 1: Vehicle Tracking Expert

Responsibilities:

- Overall technical design and implementation of the Vehicle Tracking System (VTS)

- Configuration of tracking devices with CAN bus integration

- Deployment and configuration of the cloud-based tracking platform

- Configuration of hybrid GSM/Satellite communication with international roaming

- System integration and commissioning for approximately 100 vehicles

- Ensuring cybersecurity, data integrity, and access control

- Supervising installation and testing

- Report Configuration and administration

- Conducting system administrator and end-user training

- Providing technical documentation and handover

- The Key Expert shall serve as the primary technical focal point throughout contract implementation

Qualifications and skills:

1. University degree (minimum Bachelor’s level) in:

- Telecommunications Engineering, Electronics Engineering, IT / Computer Engineering, Automotive Engineering, or other relevant technical discipline

General professional experience

1. Minimum 3 years of professional experience in vehicle telematics and/or GPS tracking

2. Participation in at least two (2) similar projects involving:

- Deployment of vehicle tracking systems

- Installation and configuration of GPS devices with CAN bus integration

- Cloud-based fleet management platforms

- Experience in at least one (1) project involving a fleet of minimum 50 vehicles

- Experience with hybrid communication systems (Cellular/mobile network and satellite-based fallback communication)

- Experience with systems operating under international roaming conditions

#### Specific professional experience

The Key Expert shall demonstrate experience with the following (or similar):

1. Hardware Integration

- CAN bus data extraction and configuration

- OBD-II or direct CAN interface modules

- Installation supervision of telematics hardware

2. Software & Cloud Systems

- Configuration of cloud-hosted fleet management platforms

- User rights management and access control configuration

- Data reporting and dashboard customization.

3. Communication Systems

- SIM management and international roaming setup

- Satellite communication fallback configuration

- Network coverage assessment and optimization.

4. Data Protection & Cybersecurity

- Secure data transmission protocols

- Cloud data hosting environments

- Role-based access control systems

- Compliance with applicable data protection regulations.

5. Language Requirements

Professional working proficiency in English

Guidance on expert time inputs:

- Working days: performance of the contract (and therefore payment) is based solely on working days. The contractor will only be paid for days actually worked on the basis of the daily fee rate contained in the budget breakdown (Annex V). The time input for experts must be expressed in Full Time Equivalent (FTE). Tenderers must annex the ‘Estimated number of working days’ worksheet contained in the spread sheet for Annex V to their organisation and methodology (Annex III) to demonstrate the correspondence between the proposed methodology and the expert inputs.

- The annual leave entitlement of the experts employed by a contractor is determined by their employment contract with the contractor and not by the service contract between the contracting authority and the contractor. However, the annual leave entitlement of experts must not exceed 60 calendar days per year. Moreover, the contracting authority can decide when experts take their annual leave since this is subject to approval by the project manager, who will assess any such request according to the needs of the project while the contract is in progress. A day of annual leave is not considered to be a working day. See Articles 21 and 22 of the general conditions.

- The fee rates for all experts must include: the remuneration paid to the experts, all the administrative costs of employing the relevant experts, such as equipment, relocation and repatriation expenses (including flights to and from the place of performance upon mobilisation and demobilisation as well as leave), accommodation, expatriation allowances, leave, medical insurance and other employment benefits given to the experts by the contractor. It shall also include any security arrangement except when this is exceptionally included under the incidental expenditure. Furthermore, the fees shall also include the margin, overheads, profit and support facilities.

- The delivery mode of the expert’s assignment is either on the place of performance or home based (see PRAG 2.5.5).  The delivery mode, and the locations where the expert will undertake missions and the working days needed for each mission are indicated in section 5.1 of the terms of reference.

### Non-key experts

The “Key Expert’s profile” (Annex IV) should not be submitted for non-key experts. However, the tenderer will have to demonstrate in their offer that they have access to experts fulfilling the minimum requirements.

The contractor must select and hire other experts as required according to the requirements in the terms of reference and as described in the submitted organisation & methodology. It must clearly indicate the category to which the experts’ belong so that the applicable daily fee rate in the budget breakdown is clear. All experts must be independent and free from conflicts of interest in the responsibilities they take on.

The selection procedures used by the contractor to select these other experts must be transparent, and must be based on pre-defined criteria, including professional qualifications, absence of professional conflicting interests, language skills and work experience. The findings of the selection panel must be recorded. The selected experts must be subject to approval by the contracting authority before the start of their implementation of tasks.

### Support staff & backstopping

The contractor will provide support facilities to their team of experts, including back-stopping, during the implementation of the contract.

Backstopping and support staff costs must be included in the fee rates.

#### General Obligation of Continuity

- The Contractor shall ensure uninterrupted performance of the services throughout the duration of the contract and any call-off contracts issued under the framework agreement.

- The Contractor shall maintain adequate organizational, technical, and personnel capacity to ensure continuity of system operation, technical support, and implementation activities.

#### Backstopping Arrangements

The Contractor shall establish appropriate backstopping arrangements to ensure continuity of expertise and service delivery in case of absence, unavailability, or replacement of the Key Expert.

Backstopping arrangements shall include, at minimum:

- Availability of suitably qualified technical personnel capable of assuming the responsibilities of the Key Expert when required

- Internal knowledge-sharing mechanisms to prevent concentration of critical system knowledge in a single individual

- Access by backstopping personnel to all relevant technical documentation, system configurations, and project records

- Clear internal escalation procedures for technical incidents

The Contractor shall describe the proposed backstopping approach in its Technical Offer.

#### Documentation & Knowledge Continuity

To ensure operational continuity, the Contractor shall:

- Maintain up-to-date technical documentation throughout contract implementation

- Document system architecture, configuration parameters, communication setup (including GSM/Satellite switching logic), and integration settings

- Maintain updated records of installed devices and their vehicle allocation

- Maintain change logs of significant system modifications.

Such documentation shall be made available to the Contracting Authority upon request and in the event of expert replacement.

#### Access Control & Administrative Rights

The Contractor shall ensure that:

- System administrator access is not limited to a single individual

- Administrative access rights are managed in a structured and secure manner

- In the event of replacement of the Key Expert, no loss of system access, control, or configuration integrity occurs.

Where applicable, the Contracting Authority shall retain appropriate administrative access rights to the cloud-based system.

#### Replacement of Key Expert

Replacement of the Key Expert shall:

- Be subject to prior written approval by the Contracting Authority

- Involve an expert with qualifications and experience at least equivalent to the key expert evaluated in the tender

- Be carried out without additional cost to the Contracting Authority

- Not result in service interruption, performance degradation, or delay in implementation.

Replacement shall not constitute grounds for modification of contractual deadlines or service level obligations.

#### Incident Escalation & Service Continuity

The Contractor shall ensure that backstopping arrangements support timely response to system incidents, including those affecting:

- Real-time vehicle monitoring

- Communication failures (GSM or Satellite)

- Cloud platform availability

- CAN data transmission.

Detailed response times and performance standards are defined in the Service Level Agreement (SLA) in Annex 1 - Requirements, point 17).

#### Business Continuity & System Resilience

Please refer to the SLA outlined in Annex 1 - Requirements, point 17).

## Office accommodation

Office accommodation of a reasonable standard and of approximately 10 square metres for each expert working on the contract is to be provided by the contractor.

The costs of the office accommodation are to be covered by the fee rates.

## Facilities to be provided by the contractor

The contractor must ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract that is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

The Contractor must have a General Liability Insurance covering any physical injury or property damage arising out of or in any way connected with the execution of the tasks herein described. In particular, the Contractor must possess an insurance that will cover the costs of any material damage suffered by EUMA vehicles while being at the Contractor’s workshop facilities or while being under the Contractor’s custody and control.

## Incidental expenditure

No expenditure verification is foreseen for this contract.

## Lump sums

No lump sums are foreseen in this contract.

# REPORTS

## Reporting requirements

Please see Article 26 of the general conditions.

There must be a final report, a final invoice and the financial report accompanied by an expenditure verification report at the end of the period of implementation of the tasks. The draft final report must be submitted at least one month before the end of the period of implementation of the tasks. Note that these interim and final reports are additional to any required in Section 4.2 of these terms of reference.

Each report must consist of a narrative section and a financial section. The financial section must contain details of the time inputs of the experts, incidental expenditure and expenditure verification.

To summaries, in addition to any documents, reports and deliverable specified under the duties and responsibilities of each key expert above, the contractor shall provide the following reports:

| Name of report | Content | Time of submission |  |
| --- | --- | --- | --- |
| Final report | Short description of the achievement of the results. The final report should include a description of the problems encountered and recommendations; a final invoice and the financial report. |  | Within 1 month of receiving comments on the draft final report from the project manager identified in the contract. |

## Submission & approval of reports

One (1) copy of the reports referred to above must be submitted to the project manager identified in the contract. The reports must be written in English. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

N/A

## Special requirements

- The maximum system failure rate must not exceed 2 % of the total input gathered.

- The system must be compatible with Windows 10 or later Microsoft type products.

- Map updates must be provided once a month and must be included in the service fee.

- Any and all collected data must be considered as sensitive information and must be handled accordingly. The Contractor must provide a description of the security measures that will be adopted to protect such information from loss, destruction, alteration, disclosure, misuse, unauthorized access, or network hacking.

# Annex 1 - Requirements

## Section 1: Mandatory General Requirements

        - For all communication and processing of data and systems, all communication shall be in English.

        - The requirement is for up to 150 vehicles (scalable) of various brands and types in various locations in Armenia, Turkey and Georgia. Vehicle types include up to 150 civilian armoured (AV) and soft skin vehicles (SSV). A detailed list of vehicles with Make and Model will be provided during the tender opening.

        - Cloud-based, no data stored on EUMA servers; the system shall be able to securely store the data on a secure server operated by the supplier as outlined in article 42 of the special conditions.

        - System to be available for authorised fleet administrators and Operation Centre operators to monitor vehicles in real time via:

          - Laptop, desktop and tablet

          - Mobile phone through the use of mobile app (iOS and Android)

          - TV-monitors (smart TV) in defined Operation Centre(s) in the various Field Missions.

        - The system shall cover Armenia, Georgia and Turkey.

        - The contractor (or its legal local dealer/representative in the various locations) shall be able and responsible to legally import, install, operate, upgrade and repair VTS elements (hardware and software) in the territory Armenia, Georgia and Turkey.

        - In case of use of a local dealer/representative, this local dealer/representative shall be able to effectively communicate (both oral and in writing) in English and/or in the local language(s).

        - The vehicle manufacturer (OEM) warranty of the vehicle(s) shall be retained after installation of the VTS.

        - The system shall be able to securely transmit data between the vehicle unit and the Operation Centre(s); further functional requirements are detailed in Section 2: Mandatory Functional Requirements.

        - Required services (hybrid signal transmission (GSM and Satellite), driver identification and vehicle immobilization) may vary, dependent on the Field Mission/Executive Structure; the finalised, mutually agreed (tailor-made) solution shall be defined with each individual purchase (Purchase Order, PO).

        - For the hybrid solution, there shall be a solution for both functionalities (GSM and satellite transmission), switching automatically between these communication channels based on availability and in order to optimise costs and notification priority.

        - System Training must be provided in English, including electronic manuals and online, incl. recording of the online training session(s).

        - At the end of the contract, the then current database must be exported to human readable tagged files and handed over to EUMA.

        - The bidder must provide, install and uninstall the system for a test phase of a minimum duration of four (4) weeks after installation and making the system available to the contracting authority, free of charge. The test phase shall include full installation of the equipment on two EUMA vehicles and full access to the website/interface with all functionalities required under the tender response. The evaluation of this test phase shall constitute an integral part of the tender evaluation. The items, aspects, and functionalities to be assessed during the test phase are detailed in Annex 2 – Evaluation Grid – Mandatory Requirements and Annex 3 – Evaluation Grid – Optional Requirements. The proposed key expert shall participate in the test phase and assume their role as defined in chapter 6.1.1.

        - Service Level Agreement – Support Services

          - The Contractor shall provide a Single Point of Contact (SPOC) for technical support, available 24 hours per day, 7 days per week, 365 days per year, accessible by email and telephone.
The SPOC shall be authorized to register incidents, initiate escalation procedures, and coordinate corrective actions.

          - Incident Classification

            - Critical Incident

              - Complete unavailability of the Vehicle Tracking System (VTS);

              - Loss of real-time fleet visibility affecting all or a substantial part of the fleet;

              - System-wide communication failure (GSM and Satellite);

              - Cloud platform inaccessible.

            - Major Incident

              - Failure of entire modules (e.g., reporting module, CAN data module);

              - Communication failure affecting a significant number of vehicles;

              - Severe degradation of system performance.

            - Minor Incident

              - Isolated device malfunction;

              - Individual vehicle data not reporting;

              - Non-critical functional issues;

              - General user inquiries.

          - Response Time (Time to Initial Acknowledgment)

Measured from the time the incident is reported to the SPOC:

            - Critical: Maximum 1 hour

            - Major: Maximum 4 hours

            - Minor: Maximum 12 hours

Response time means acknowledgment of the incident, assignment of a reference number, and initiation of corrective action.

          - Correction Time (Time to Resolution or Workaround)

Measured from the time of incident registration:

            - Critical: Maximum 12 hours

            - Major: Maximum 24 hours

            - Minor: Best effort, to be resolved within reasonable time

Correction time means restoration of service or implementation of an acceptable workaround agreed with the Contracting Authority.

          - Compensation Mechanisms

Failure to meet the above response or correction times in more than 5% of the submitted requests per calendar month shall result in service credits calculated as follows:

            - Critical Incidents

              - Failure to meet response time: 5% of monthly service fee

              - Failure to meet correction time: 10% of monthly service fee

            - Major Incidents

              - Failure to meet response time: 3% of monthly service fee

              - Failure to meet correction time: 5% of monthly service fee

            - Cap

Total service credits in a given month shall not exceed 15% of the monthly service fee.
Service credits shall be deducted from the next invoice or via debit note.

          - Post-installation services (consultations, review of system, etc.);

          - Before upgrading/changing the system (software application), this has to be announced in advance, while providing a ‘test environment’, before going ‘live’.

## Section 2: Mandatory Functional Requirements

- Geographical position/coordinates of the vehicle; the system is to graphically reflect the actual vehicle position on (satellite) maps of the corresponding area;

- Real time vehicle monitoring, collecting and submitting information; the system shall allow monitoring in real-time the status of each vehicle in the fleet on:

  - Identification of the driver;

  - Geographical position/coordinates of the vehicle;

  - Ignition is turned on/off; actual times;

  - Engine is on/off; actual times;

  - Vehicle Speed/Velocity and heading (direction);

  - Trajectory; plotting the path travelled over a digital map background.

- To facilitate/enable collection of vehicle data as set out in the previous point, automated vehicle sensor information feed (for instance through Controller Area Network bus, CAN bus or equal alternative) from on-board computer (OBDII or alternative) should be supported if the vehicle is equipped with CAN-Bus.

- Regarding the previous point, the supplier shall be able to identify the presence of a CAN-Bus based on the VIN provided by the contracting authority.

- Provide automatic driver identification (driver’s ID) using RFID technology (preferably and integrated with credit card format EUMA driver permit) or – alternatively – Dallas Key/Swipe Card; the RFID/Dallas Key allocated to the driver will determine the ‘driver rights’, i.e. which (category/type of) vehicles can be driven by that driver. The system has a white list containing drivers and that can be administered and modified by the contracting authority; in case a driver tries to identify who is not in the white list, the system emits an audible warning in the vehicle concerned and sends a notification to a recipient that can be defined by the contracting authority.

- Provide 300 identification items (RFID-cards. Dallas keys etc.) and the possibility to provide more upon receiving an order from the contracting authority (price as per the financial offer).

- Vehicle Immobilisation in case of unauthorised driver; the contracting authority should be able to deactivate this feature from their user platform for the entire fleet or parts of it.

- Emergency/Panic button functionality for emergency cases; emergency button to be positioned within reach of both the driver and the co-driver, but activation should be possible without being noticed from outside the vehicle.

- Covert-In-Installation;

  - equipment should not be directly visible by driver/passengers and outside observers while operating the vehicle;

  - visibility and maneuverability of the driver should not be negatively affected;

  - (smart) devices should consist of compact outdoor (discrete communications and navigation antenna) and indoor unit(s) connected to the vehicle battery and ensure collecting information from navigation satellites and any other input sources (including on-board computer) as per functional requirements below and transmitting this information to the respective Operation Centre(s) in the various Field Missions.

- Ability to define geo-fencing for each individual vehicle.

- Audible alert in case of:

  - Attempt to start the vehicle without positive driver identification; The system shall use a whitelist for drivers in case RFID cards/Dallas Keys/any other identifier are used to prevent drivers use other than the identifier contained in the whitelist. This whitelist must be adjustable by the administrator of the system at the contracting authority.

  - Geo-Fence violation; the geo-fence feature is to initiate immediate alerts/notification when a vehicle exits or enters a pre-defined geographical area;

  - Over speeding; to notify when a vehicle exceeds a pre-set maximum speed for the vehicle for more than a predefined tolerance time;

  - Low Battery; when the battery voltage reaches a pre-defined low level.

  - Driver Whitelist event: when an unauthorized/unidentified driver uses the vehicle the sound alert must function without interruption until the vehicle engine is off or the driver identifies with the correct means of identification contained in the whitelist.

- In case the vehicle voltage drops below a pre-defined threshold and to avoid full drainage of vehicle battery/batteries, the system shall switch to a reduced power consumption pattern and eventually cut-off the power of VTS entirely.

- The driver whitelist must allow layers editing, e.g. drivers that can drive all vehicles and drivers that can drive only a limited group of vehicles (soft skin vs hard skin vehicles, manual vs automatic transmission, etc).

- Driver administration:

  - The system must allow bulk uploads in a preset template for creating / editing;

  - Editing should be possible both one by one and in bulk;

  - The system must be able to create different driver groups, which are related to vehicle groups and the different whitelist layers;

  - The system must allow any driver in the whitelist to be set as active or inactive, e.g. when a driver has the driver’s license suspended;

  - The system must contain at least the following fields: name, position, place of deployment, e-mail, phone, RFID / Dallas key code, personal ID code, driving license category, normal working hours / shift working hours, status (active / inactive).

- Vehicle administration:

  - The system must allow bulk uploads in a preset template for creating / editing;

  - Editing should be possible both one by one and in bulk;

  - The system must be able to create different vehicle groups, which are related to driver groups and the different whitelist layers;

  - The system must allow vehicles to be set active or inactive, e.g. when a vehicle is damaged or needs maintenance / repairs;

  - The system must contain at least the following fields: type (soft skin / hard skin), make, model, license plate number, place of deployment, normal usage hours / shift usage hours, status (active / inactive), odometer.

  - For vehicles with CAN-bus, the system should read the odometer automatically, but in any case the system should allow the administrator to correct / edit the odometer manually and to estimate the odometer at any point, based on the last edit of odometer and the distance recorded as driven from that moment.

- Mapping:

  - Information provided by the system shall be overlaid onto a digital base map, accessible from a web browser not requiring additional software to be installed on users’ computers;

  - The system is to provide the user with the option to use either a ‘vector’ base map – e.g. a satellite imagery, or a raster base map. Labels should also be displayed on (overlaid on top of) the satellite imagery base map;

  - The system is to provide the user the choice whether vehicles are grouped on the map when close together or not.

  - The system is to provide the user with the option to display or hide labels on the base map, with the default being display labels;

  - The digital base map is to display up-to-date information about road networks and location/region names;

  - Users are to be able to zoom in the base map to street level – displaying the road network – and zoom out to display the digital base map up to international borders. Labelling of roads/locations should be appropriate to the zoom level;

  - The system is to facilitate the filtering of information displayed on the digital base map by:

    - user rights e.g. user X is only permitted to view/track vehicles from one or more groups of vehicles;

    - user-selection of one or more groups of vehicles they have access to;

    - users should be able to manually filter the vehicles displayed using vehicle make and/or model, (partial) vehicle registration number, and other search criteria provided by the system;

  - The system shall allow configuration of regions of interest (ROIs) and points of interest (POIs) including easy notification of a vehicle entering and leaving ROIs and/or POIs and including subsequent relevant time recordings (when a vehicle entered and left a specific region/point).

  - Possibility to save frequently used views for simplified (easy and quick) access, also as ‘bulk-editing’ for a group/fleet of vehicles;

  - When refreshing the map (automatically or manually) the previous map setting (scaling, map type, selected vehicles) shall be maintained.

- Signaling:

  - Frequency of signaling shall be as frequent as possible but not less than one emission every 30 seconds in GSM/GPRS mode and 30 minutes in satellite mode to allow for timely/adequate and accurate position, speed and distance travelled and can be dependent on speed (higher frequency of signal with higher speed);

  - The system shall switch automatically to satellite signaling when GSM signal is weak/interrupted;

  - Possibility to disable GSM roaming for specific vehicles;

  - Ability to ‘store’ information in case of loss of GSM/GPRS signal; the stored information shall be transmitted immediately after the GSM/GPRS -signal has been restored;

  - Data (transmission) to be secured by adequate encryption and authentication methods.

- Reporting:

  - The system must be able to export all reports at least as a Microsoft Excel file, with a database format (one header at the top followed by the reported data underneath).

  - User access control – access to vehicle data for users to be user-defined and based on user privileges (fleet/group membership)

  - Per trip report: vehicle license plate, driver, distance, average speed, maximum speed, start/end timings/duration of trip

  - Per trip report: creator must offer the possibility to filter on the following:

    - date and time periods,

    - distance travelled in the given period,

    - groups of vehicles and groups of drivers e.g. report contains all trips longer than a given mileage per day (e.g. 50 km/day)

  - Per driver report for any given period of time:

    - number of trips

    - total distance travelled

    - vehicles used

    - start/end timings/duration of trips

  - Per driver report: creator must offer the possibility to filter on

    - date and time periods

    - distance travelled in the given period

    - groups of vehicles and groups of drivers e.g. report contains all trips longer than a given mileage per day (e.g. 50 km/day)

  - Per vehicle report:

    - vehicle

    - driver

    - distance

    - average speed

    - maximum speed

    - start/end timings/duration

  - Per vehicle report creator must offer the possibility to filter on

    - date and time periods

    - distance travelled and

    - all drivers in the given period, e.g. report contains all trips longer than a given mileage per day for the last given number of months

  - Distances travelled shall be identical to the odometer readings if the vehicle is equipped with a CAN-BUS

  - Ability to produce both regular and ad hoc reports

  - Possibility to schedule (auto-generated, pre-set frequency) reports to pre-defined recipients;

  - Enabling API (application programming interface) for up/downloading of aggregated information from VTS/GPS to Fleet Management software currently in use at the contracting authority.

  - All vehicle data (including vehicle utilization and driving history) to be stored and remain available for the entire duration of the contract; after ending of contract data to be provided to EUMA on a digital storage device (hard disk).

- Alert/alarm notifications:

  - The interface must have an automated alert system.

  - The alert / alarms system must be able to send notifications in the interface and e-mail to preset users, and/or SMS / phone messages to preset users.

  - The user list that receives alerts must be editable and must allow receiving alerts from all the fleet or only from a defined group of vehicles or drivers depending on the responsibilities / privileges of the user.

  - The system must be able to generate configurable automatic alerts / alarms at least for:

    - unidentified driver

    - entering / exiting POI and ROI

    - overspeeding

    - panic button

## Section 3: Personal Data Protection

In addition to the EUMA General Conditions of Contract, the following applies to the processing of personal data related to the contract as well as contract implementation (meaning processed via the vehicle tracking system):

            - The Contractor shall process all personal data in accordance with Regulation and Regulation (EU) 2016/679.

            - All personal data must be stored on servers located in a member state of the European Union.

            - No personal data shall be shared with third parties without the consent of the Contracting Authority.

# Annex 2 – Evaluation Grid – Mandatory Requirements

| 1 | 2 | 3 |
| --- | --- | --- |
| Item number | Service | Quantity of vehicles |
|  | For all communication and processing of data and systems, all communication shall be in English. | 100 |
|  | The requirement is for up to 150 vehicles (scalable) of various brands and types in various (field) locations. Vehicle types include civilian armoured vehicles and soft skin vehicles. A detailing of vehicles with Make and Model for each geographical location will be provided during the tender opening. | 100 |
|  | Cloud based, no data stored on EUMA servers; the system shall be able to securely store the data on a secure server operated by the supplier as outlined in article 42 of the special conditions. | 100 |
|  | System to be available for authorised fleet administrators and Operation Centre operators to monitor vehicles in real time via: - Laptop, desktop and tablet - Mobile phone through the use of mobile app (iOS and Android) - TV-monitors (smart TV) in defined Operation Centre(s) in the various Field Missions. | 100 |
|  | The system shall cover the territory of Armenia, Georgia and Turkey. | 100 |
|  | The contractor (or its legal local dealer/representative in Armenia) shall be able and responsible to legally import, install/de-install (old hardware), operate, upgrade, repair and warrant VTS elements (hardware and software) in the territory of Armenia, Georgia and Turkey. | 100 |
|  | In case of use of a local dealer/representative, this local dealer/representative shall be able to effectively communicate (both oral and in writing) in either English or in the local language(s). | 100 |
|  | The vehicle manufacturer (OEM) warranty of the vehicle(s) shall be retained after installation of the VTS. | 100 |
|  | The system shall be able to securely transmit data between the vehicle unit and the Operation Centre(s); further functional requirements are detailed in Section 2: Mandatory Functional Requirements. | 100 |
|  | Required services (hybrid signal transmission (GSM and Satellite), driver identification and vehicle immobilization) may vary, dependent on the Field Mission/Executive Structure; the finalised, mutually agreed (tailor-made) solution shall be defined with each individual purchase (Purchase Order, PO). | 100 |
|  | For the hybrid solution, there shall be a solution for both functionalities (GSM and satellite transmission), switching automatically between these communication channels based on availability and in order to optimise costs and notification priority. | 100 |
|  | System Training must be provided in English, including electronic manuals and online, incl. recording of the online training session(s). | 100 |
|  | At the end of the contract, the then current database must be exported to human readable tagged files and handed over to EUMA. | 100 |
|  | The bidder must provide, install and uninstall the system for a test phase of a minimum duration of four (4) weeks after installation and making the system available to the contracting authority, free of charge. The test phase shall include full installation of the equipment on two EUMA vehicles and full access to the website/interface with all functionalities required under the tender response. The evaluation of this test phase shall constitute an integral part of the tender evaluation. The items, aspects, and functionalities to be assessed during the test phase are detailed in Annex 2 – Evaluation Grid – Mandatory Requirements and Annex 3 – Evaluation Grid – Optional Requirements. The proposed key expert shall participate in the test phase and assume their role as defined in chapter 6.1.1. | 2 |
|  | Service Level Agreement – Support Services - The Contractor shall provide a Single Point of Contact (SPOC) for technical support, available 24 hours per day, 7 days per week, 365 days per year, accessible by email and telephone. The SPOC shall be authorized to register incidents, initiate escalation procedures, and coordinate corrective actions. - Incident Classification - Critical Incident - Complete unavailability of the Vehicle Tracking System (VTS); - Loss of real-time fleet visibility affecting all or a substantial part of the fleet; - System-wide communication failure (GSM and Satellite); - Cloud platform inaccessible. - Major Incident - Failure of entire modules (e.g., reporting module, CAN data module); - Communication failure affecting a significant number of vehicles; - Severe degradation of system performance. - Minor Incident - Isolated device malfunction; - Individual vehicle data not reporting; - Non-critical functional issues; - General user inquiries. - Response Time (Time to Initial Acknowledgment) Measured from the time the incident is reported to the SPOC: - Critical: Maximum 1 hour - Major: Maximum 4 hours - Minor: Maximum 12 hours Response time means acknowledgment of the incident, assignment of a reference number, and initiation of corrective action. - Correction Time (Time to Resolution or Workaround) Measured from the time of incident registration: - Critical: Maximum 12 hours - Major: Maximum 24 hours - Minor: Best effort, to be resolved within reasonable time Correction time means restoration of service or implementation of an acceptable workaround agreed with the Contracting Authority. - Compensation Mechanisms Failure to meet the above response or correction times in more than 5% of the submitted requests per calendar month shall result in service credits calculated as follows: - Critical Incidents - Failure to meet response time: 5% of monthly service fee - Failure to meet correction time: 10% of monthly service fee - Major Incidents - Failure to meet response time: 3% of monthly service fee - Failure to meet correction time: 5% of monthly service fee - Cap Total service credits in a given month shall not exceed 15% of the monthly service fee. Service credits shall be deducted from the next invoice or via debit note. - Post-installation services (consultations, review of system, etc.); - Before upgrading/changing the system (software application), this has to be announced in advance, while providing a ‘test environment’, before going ‘live’. | 100 |
|  | Geographical position/coordinates of the vehicle; the system is to graphically reflect the actual vehicle position on (satellite) maps of the corresponding area | 100 |
|  | Real time vehicle monitoring, collecting and submitting information; the system shall allow monitoring in real-time the status of each vehicle in the fleet on: - Identification of the driver; - Geographical position/coordinates of the vehicle; - Ignition is turned on/off; actual times; - Engine is on/off; actual times; - Vehicle Speed/Velocity and heading (direction); - Trajectory; plotting the path travelled over a digital map background. | 100 |
|  | To facilitate/enable collection of vehicle data as set out in the previous point, automated vehicle sensor information feed (for instance through Controller Area Network bus, CAN bus or equal alternative) from on-board computer (OBDII or alternative) should be supported if the vehicle is equipped with CAN-Bus. |  |
|  | Regarding the previous point, the supplier shall be able to identify the presence of a CAN-Bus based on the VIN provided by the contracting authority. | 100 |
|  | Provide automatic driver identification (driver’s ID) using RFID technology (preferably and integrated with credit card format EUMA driver permit) or – alternatively – Dallas Key/Swipe Card; the RFID/Dallas Key allocated to the driver will determine the ‘driver rights’, i.e. which (category/type of) vehicles can be driven by that driver. The system has a white list containing drivers and that can be administered and modified by the contracting authority; in case a driver tries to identify who is not in the white list, the system emits an audible warning in the vehicle concerned and sends a notification to a recipient that can be defined by the contracting authority. |  |
|  | Provide 300 identification items (RFID-cards. Dallas keys etc.) and the possibility to provide more upon receiving an order from the contracting authority (price as per the financial offer). | 100 |
|  | Vehicle Immobilisation in case of unauthorised driver; the contracting authority should be able to deactivate this feature from their user platform for the entire fleet or parts of it. | 100 |
|  | Emergency/Panic button functionality for emergency cases; emergency button to be positioned within reach of both the driver and the co-driver, but activation should be possible without being noticed from outside the vehicle. | 100 |
|  | Covert-In-Installation; - equipment should not be directly visible by driver/passengers and outside observers while operating the vehicle; - visibility and maneuverability of the driver should not be negatively affected; - (smart) devices should consist of compact outdoor (discrete communications and navigation antenna) and indoor unit(s) connected to the vehicle battery and ensure collecting information from navigation satellites and any other input sources (including on-board computer) as per functional requirements below and transmitting this information to the respective Operation Centre(s) in the various Field Missions. | 100 |
|  | Ability to define geo-fencing for each individual vehicle. | 100 |
|  | Audible alert in case of: - Attempt to start the vehicle without positive driver identification; The system shall use a whitelist for drivers in case RFID cards/Dallas Keys/any other identifier are used to prevent drivers use other than the identifier contained in the whitelist. This whitelist must be adjustable by the administrator of the system at the contracting authority. - Geo-Fence violation; the geo-fence feature is to initiate immediate alerts/notification when a vehicle exits or enters a pre-defined geographical area; - Over speeding; to notify when a vehicle exceeds a pre-set maximum speed for the vehicle for more than a predefined tolerance time; - Low Battery; when the battery voltage reaches a pre-defined low level. - Driver Whitelist event: when an unauthorized/unidentified driver uses the vehicle the sound alert must function without interruption until the vehicle engine is off or the driver identifies with the correct means of identification contained in the whitelist. | 100 |
|  | In case the vehicle voltage drops below a pre-defined threshold and to avoid full drainage of vehicle battery/batteries, the system shall switch to a reduced power consumption pattern and eventually cut-off the power of VTS entirely. | 100 |
|  | The driver whitelist must allow layers editing, e.g. drivers that can drive all vehicles and drivers that can drive only a limited group of vehicles (soft skin vs hard skin vehicles, manual vs automatic transmission, etc). |  |
|  | Driver administration: - The system must allow bulk uploads in a preset template for creating / editing; - Editing should be possible both one by one and in bulk; - The system must be able to create different driver groups, which are related to vehicle groups and the different whitelist layers; - The system must allow any driver in the whitelist to be set as active or inactive, e.g. when a driver has the driver’s license suspended; - The system must contain at least the following fields: name, position, place of deployment, e-mail, phone, RFID / Dallas key code, personal ID code, driving license category, normal working hours / shift working hours, status (active / inactive). |  |
|  | Vehicle administration: - The system must allow bulk uploads in a preset template for creating / editing; - Editing should be possible both one by one and in bulk; - The system must be able to create different vehicle groups, which are related to driver groups and the different whitelist layers; - The system must allow vehicles to be set active or inactive, e.g. when a vehicle is damaged or needs maintenance / repairs; - The system must contain at least the following fields: type (soft skin / hard skin), make, model, license plate number, place of deployment, normal usage hours / shift usage hours, status (active / inactive), odometer. - For vehicles with CAN-bus, the system should read the odometer automatically, but in any case the system should allow the administrator to correct / edit the odometer manually and to estimate the odometer at any point, based on the last edit of odometer and the distance recorded as driven from that moment. |  |
|  | Mapping: - Information provided by the system shall be overlaid onto a digital base map, accessible from a web browser not requiring additional software to be installed on users’ computers; - The system is to provide the user with the option to use either a ‘vector’ base map – e.g. a satellite imagery, or a raster base map. Labels should also be displayed on (overlaid on top of) the satellite imagery base map; - The system is to provide the user the choice whether vehicles are grouped on the map when close together or not. - The system is to provide the user with the option to display or hide labels on the base map, with the default being display labels; - The digital base map is to display up-to-date information about road networks and location/region names; - Users are to be able to zoom in the base map to street level – displaying the road network – and zoom out to display the digital base map up to international borders. Labelling of roads/locations should be appropriate to the zoom level; - The system is to facilitate the filtering of information displayed on the digital base map by: - user rights e.g. user X is only permitted to view/track vehicles from one or more groups of vehicles; - user-selection of one or more groups of vehicles they have access to; - users should be able to manually filter the vehicles displayed using vehicle make and/or model, (partial) vehicle registration number, and other search criteria provided by the system; - The system shall allow configuration of regions of interest (ROIs) and points of interest (POIs) including easy notification of a vehicle entering and leaving ROIs and/or POIs and including subsequent relevant time recordings (when a vehicle entered and left a specific region/point). - Possibility to save frequently used views for simplified (easy and quick) access, also as ‘bulk-editing’ for a group/fleet of vehicles; - When refreshing the map (automatically or manually) the previous map setting (scaling, map type, selected vehicles) shall be maintained. | 100 |
|  | Signaling: - Frequency of signaling shall be as frequent as possible but not less than one emission every 30 seconds in GSM/GPRS mode and 30 minutes in satellite mode to allow for timely/adequate and accurate position, speed and distance travelled and can be dependent on speed (higher frequency of signal with higher speed); - The system shall switch automatically to satellite signaling when GSM signal is weak/interrupted; - Possibility to disable GSM roaming for specific vehicles; - Ability to ‘store’ information in case of loss of GSM/GPRS signal; the stored information shall be transmitted immediately after the GSM/GPRS -signal has been restored; - Data (transmission) to be secured by adequate encryption and authentication methods. | 100 |
|  | Reporting: - The system must be able to export all reports at least as a Microsoft Excel file, with a database format (one header at the top followed by the reported data underneath). - User access control – access to vehicle data for users to be user-defined and based on user privileges (fleet/group membership) - Per trip report: vehicle license plate, driver, distance, average speed, maximum speed, start/end timings/duration of trip - Per trip report: creator must offer the possibility to filter on the following: - date and time periods, - distance travelled in the given period, - groups of vehicles and groups of drivers e.g. report contains all trips longer than a given mileage per day (e.g. 50 km/day) - Per driver report for any given period of time: - number of trips - total distance travelled - vehicles used - start/end timings/duration of trips - Per driver report: creator must offer the possibility to filter on - date and time periods - distance travelled in the given period - groups of vehicles and groups of drivers e.g. report contains all trips longer than a given mileage per day (e.g. 50 km/day) - Per vehicle report: - vehicle - driver - distance - average speed - maximum speed - start/end timings/duration - Per vehicle report creator must offer the possibility to filter on - date and time periods - distance travelled and - all drivers in the given period, e.g. report contains all trips longer than a given mileage per day for the last given number of months - Distances travelled shall be identical to the odometer readings if the vehicle is equipped with a CAN-BUS - Ability to produce both regular and ad hoc reports - Possibility to schedule (auto-generated, pre-set frequency) reports to pre-defined recipients; - Enabling API (application programming interface) for up/downloading of aggregated information from VTS/GPS to Fleet Management software currently in use at the contracting authority. - All vehicle data (including vehicle utilization and driving history) to be stored and remain available for the entire duration of the contract; after ending of contract data to be provided to EUMA on a digital storage device (hard disk). | 100 |
|  | Alert/alarm notifications: - The interface must have an automated alert system. - The alert / alarms system must be able to send notifications in the interface and e-mail to preset users, and/or SMS / phone messages to preset users. - The user list that receives alerts must be editable and must allow receiving alerts from all the fleet or only from a defined group of vehicles or drivers depending on the responsibilities / privileges of the user. - The system must be able to generate configurable automatic alerts / alarms at least for: - unidentified driver - entering / exiting POI and ROI - overspeeding - panic button |  |
|  | The Contractor shall process all personal data in accordance with Regulation and Regulation (EU) 2016/679. |  |
|  | All personal data must be stored on servers located in a member state of the European Union. |  |
|  | No personal data shall be shared with third parties without the consent of the Contracting Authority. |  |