## Slide 1
Mid-Term Evaluation for the Tourism-Led Model for Local Economic Development Support Programme
Tourism-Led Model for Local Economic Development Support programme
AITP was designed to address major structural constraints affecting tourism development in Albania’s inland and culturally rich regions. Through a financing package of EUR 105 million combining EU grants with EBRD sovereign loans and financial instruments, the programme adopted an ambitious integrated approach bringing together tourism development, infrastructure, heritage restoration, MSME support and inclusion measures within a single initiative.
The overall objective of Tourism-Led Model for Local Economic Development Support Programme is to improve the competitiveness and economic growth of Albania through high-quality and sustainable tourism, in line with the National Strategy for Development and Integration.
The specific objectives and expected results, as stated in the programming documentation, are linked to increasing quality and sustainability of the integrated tourism offers in four pilot territories (Berat, Fier, Korça, Shkodër); Enhance and preserve the attractiveness of cultural, natural and other assets in the pilot territories; Improve the local sustainable development of priority infrastructure and its climate resilience within Albania’s regional development policy and provide access to finance to local MSMEs to increase their competitiveness in the Albanian economy. Implementation period from 2018 to 2027 and budget a 40 million euro grant from the EU combined with a 60 million euro loan from the EBRD.

## Slide 2
Mid-Term Evaluation for the Tourism-Led Model for Local Economic Development Support Programme
Main findings
The projects correctly identified the main barriers limiting sustainable tourism growth.
The project continue to be highly relevant for Albania’s tourism and regional development priorities
The programme demonstrates strong EU added value as it combines grants, loans and technical assistance
The original vision for a comprehensive programme was limited by significant initial delays and limited coordination across components
The opportunity the project provided to strengthen the policy dialogue on tourism both locally and at central level has not been sufficiently capitalised upon
Lessons learnt
The implementation of the programme was focused on individual municipalities in a country as small as Albania, a focus on regional development could have further strengthened the impact of the activities.
A strong focus on the governance structures for instance through a single led implementation structure is needed in projects like this one, which combines loans, grants and technical assistance
The baseline should have been established in the initial phases of the project and a much stronger focus on data collection would have benefitted the communication on impact.
Recommendations
Accelerating implementation of delayed infrastructure projects through a dedicated risk management and acceleration plan;
Strengthening sustainability arrangements, municipal ownership and maintenance planning for completed assets;
Improving coordination and information-sharing across programme components;
Reinforcing monitoring systems and outcome-level reporting;
Strengthening communication and visibility by presenting AITP as a single integrated EU–EBRD initiative