SCOPE OF WORKS

for the Design and Build of a Maritime Police Station, Perimeter wall and latrine block in Bosaso, Puntland, Somalia.

Introduction

The purpose of this Scope of Works is to define the scope, objectives, and requirements for the Design and Build of a Maritime Police Station in Bossaso, Puntland.

This document provides an overview of the project context, current condition of the site, and the key technical, functional, and spatial parameters that will guide the preparation of the detailed design documentation and Construction of the Maritime Police Station, Perimeter wall and latrine block.

The Scope of Works is prepared by EUCAP Somalia in close coordination with the PMPF, financed by the EUCAP Somalia.

- Summary

- Title of Project: Design and Build of a Maritime Police Station, Perimeter wall and latrine block for Puntland Maritime Police Force (PMPF)

- Duration of Works: Nine (9) months from date of contract signing

- Project Site / Location of Works: Bossaso, Puntland, Somalia

The total land area: 25,200 m².

- Project Name: Strengthening the operational capacities of the PMPF

  - Context and background

This assignment is financed by EUCAP Somalia and implemented by EUCAP Somalia in cooperation with the PMPF.

Due to its operational significance, the construction of the Maritime Police Station will enhance the PMPF in the maritime police capability, which will allow them to monitor their area of operations and/or collect/exchange information with other regional and/or international bodies.

The project aims to reinforce the operational capacities of the PMPF by:

  - Design and building a new Maritime Police Station including office space, training area, changing room, operation room with renewable energy facilities, access for disables people, eco-proof design, efficient waste management system, use of local materials

  - Construction of a Perimeter wall ensuring safe and secure environment

The site is free from existing construction.

  - Project Objectives

    - Objective

The objective of this assignment is the preparation of a complete technical design documentation and construction for a Maritime Police Station, Perimeter wall and latrine block, in accordance with the applicable national legislation and EUCAP Somalia requirements.

The construction is limited to interventions within the specified site and construction of a Maritime Police Station, the perimeter wall and latrine block (composed by 4 toilet) detached from the main building.

    - Scope of the Assignment

The Contractor shall:

- Verify the existing condition of the site through site visits, measurements and technical assessment;

- Prepare all required baseline technical inputs necessary for design development, including land survey, geotechnical investigations and other studies required by regulation;

- Develop coordinated multidisciplinary design solutions covering all required disciplines (architectural, structural, electrical, mechanical, water supply and sewerage, fire protection, energy efficiency, health and safety and other required documentation);

- Define technical solutions for the construction of the Maritime Police station, perimeter wall and latrine block;

- Deliver Final Design to include Bill of Quantities ensuring economic efficiency of the investment and rational selection of materials and systems, all in consultation with EUCAP Somalia;

- Propose a phased implementation concept

- Implement the construction of the Maritime Police Station, Perimeter wall and latrine block

- Handing over the construction including instruction`s manual, as built drawings and maintenance plan.

Any additional measures shall be limited to those technically necessary to ensure safe and durable execution of the defined construction scope.

    - Expected results

- All required baseline studies and documentation, including, but not limited to land survey, parcellation elaboration documentation, geotechnical investigation, and all other relevant documentation needed for this specific technical design development;

- Completed Final Design suitable for EUCAP Design review and national review and subsequent building-permit procedures;

- Technical documentation ready for building-permit issuance if requested;

- Construction of the Maritime Police Station, perimeter wall and latrine block as per submitted timeline activities in compliance with international standards as specified in the technical specifications document.

  - Stakeholders and responsibilities

Key stakeholders

- PMPF - Main beneficiary and End user;

- EUCAP Somalia - Project financier;

- Contractor - Designer and construction implementer under Contract;

- EUCAP Somalia – contracting authority.

Roles and responsibilities

EUCAP Somalia: Overall project management; coordination of design process; quality control.

Contractor: Preparation of complete technical documentation in accordance with this Scope of Works and applicable legislation; coordination of all design disciplines; submission of Final Design within contractual deadlines; coordination with the reviewer (EUCAP) and incorporation of all review comments; preparation of Bill of Quantities, approved by EUCAP Somalia; definition of phased execution concept ; implementation of the Works; handing over of the building, perimeter wall and latrine block.

Reporting and Communication Requirements

The Contractor shall:

- Participate in weekly coordination meetings with EUCAP Somalia during active design stages and implementation phase.

- Submit a Final Completion Report upon delivery of the Final Design.

- Organise ad-hoc technical meetings prior to major milestones during the implementation phase.

- Submit weekly advancement report to the Contracting authority (EUCAP)

- Submit structured Progress Reports at to major construction stages, summarising:

    - completed activities,

    - outstanding issues,

    - key technical decisions,

    - identified risks and proposed resolutions.

  - Previous research undertaken and outcomes

No formal technical surveys have been conducted within the scope of this assignment.

A preliminary design concept was prepared by the EUCAP Technical Team in 2024. The documentation will be attached to the Scope of Works and available for the contractor.

The Contractor shall independently verify all dimensions, structural systems, installations and construction assemblies through on-site measurements and technical assessment within 30 days from Contract signature.

Feasibility study is not required.

- Site information

This section provides an overview of the physical and operational characteristics of the project site relevant for design development and implementation.

The site is in the vicinity of Bossaso Airport. Vehicular and service access to the site is permitted through the airport and is available between 6:30 AM and 5:00 PM. Due to the distance between the airport entrance and the proposed police station site, pedestrian access is not feasible. Therefore, the contractor shall arrange their own transportation for the movement of labour and personnel to and from the site.

  - Physical

Location and Elevation

Approximate coordinates of the site:

| Point | Coordinats |
| --- | --- |
| Point A | 11016'59.72'' N 4909'26.57'' E |
| Point B | 11017'1.06'' N 4909'33.39'' E |
| Point C | 11017'4.90'' N 4909'32.68'' E |
| Point D | 11017'3.63'' N 4909'25.85'' E |

Elevation: approx. 2m at shoreline, 5m at the front wall along the road

Topography and terrain

The terrain slopes downward shoreline

Geotechnical and geological considerations

No geotechnical investigations have yet been performed.

Visible site conditions indicate:

- The soil is brownish in colour and non-cohesive

- The soil is a coarse-grained soil with very low fines (silt/clay)

- Topsoil is relatively fine, but the strata may change downwards

Geotechnical and engineering-geological investigations shall be performed as part of the design phase.

Hydrology and drainage

The site is generally flat, with a gradual downward slope toward the northern side, leading to the shoreline. This natural topography allows stormwater drainage to be feasibly directed toward the sea through appropriate site levelling and slope adjustments. Where necessary, localized cutting and filling shall be undertaken to establish adequate gradients, ensuring that site drainage is conveyed northwards toward the sea in a controlled manner.

Existing Structures (Physical Condition Overview)

No existing structure present on the selected site

Surrounding Context

The project site is bordered by the sea to the north, while Airport Road runs along its southern boundary. To the west, the site adjoins an existing fenced property, and an open, undeveloped area to the east.

  - Economic

Construction materials required for the reconstruction are generally available on the local market (imported). Standard materials can be sourced locally, while specialised structural or technical systems may require regional/ international procurement.

The Contractor shall ensure that proposed technical solutions are economically rational.

EUCAP Somalia must approve all materials, equipment and technical systems selected.

Long-term operation and maintenance costs shall be considered when selecting materials and systems.

  - Environmental

Climate and natural conditions

Bossaso is characterised by long and warm, high seasonal humidity and significant precipitation. The site is located at average of 3.5m above sea level, which contributes to prolonged low-temperature exposure and freeze–thaw stress on building envelopes and ground-contact elements.

- These climatic conditions directly affect durability of facades, waterproofing systems and structural elements.

Environmental risks Identified on Site

Observed site conditions include:

- absence of functional stormwater drainage and sewage,

- persistent surface runoff toward the shoreline,

- capillary moisture affecting ground-contact walls and basement zones,

- Proximity to the sea, exposing materials to a corrosive marine environment; therefore, anti-rust galvanized steel should be used for all steel elements.

Landscape, ecology and flora

The site is empty plot, close to the airport entrance, not urbanised. Vegetation is limited to minor landscaped areas. No protected flora or fauna have been identified.

Resource and Energy Considerations

The site is connected to municipal infrastructure networks, including electricity and water supply systems. However, the design shall consider the establishment of proper connections from the main power line and water supply network to the site.

Design development shall consider durability, energy efficiency and reduction of moisture-

related deterioration in line with applicable national regulations.

  - Logistical

Basis of Information

The logistical information provided in this section is based on observations from the site visit and currently available documentation.

The Contractor remains responsible for independently verifying all site conditions and identifying any additional logistical constraints relevant to design development and implementation.

Site Access

The site is currently open with no existing perimeter fencing. The construction of temporary fencing is optional prior to the construction of the permanent concrete block perimeter wall.

During the construction phase, the temporary fencing (if installed) shall incorporate one vehicular access gate along with a dedicated pedestrian access point to facilitate site entry and movement.

Site Constraints

At the actual stage there is no space for staging, storage and equipment placement.

Operational Condition

The PMPF Police Station project is at proposal stage. Nothing implemented yet.

A construction phasing diagram (Gantt chart or similar) shall be prepared as part of the Final Design, reflecting realistic sequencing of works. This diagram must be sufficiently detailed for subsequent construction works.

  - Security

The project site is located within vicinity of Bender-Qasim Airport Bossaso. At the moment, there are no risks related to armed conflict, terrorism, civil unrest, organised violence, or explosives contamination.

The selected site is empty and not fenced but the access is generally controlled through defined

No significant security incidents have been reported in relation to the selected site.

The Contractor shall verify existing site access conditions and security arrangements as part of the initial site assessment.

- Design Proposals

The Design Proposal defines the technical framework for the construction of the Maritime Police Station, in accordance with the EUCAP Technical Specifications and applicable legislation.

The primary objectives are the detailed design of the facility together with floor assemblies and all building systems and the construction of the new Maritime Police Station, perimeter wall and latrine block.

  - Functional overview and proposal

Functional Overview

The work consists of designing and constructing an administrative building that meets the needs of a modern police station.

The building's architecture will be of the 3 multi-storey building, with a total area of ​​approximately 147 sqm. The load-bearing structure will be made of reinforced concrete; the brick walls do not have a load-bearing role, serving only to close the empty spaces between the frames.

The Police station building will have:

| Floor | Functionality | No. of rooms |
| --- | --- | --- |
| Ground floor | - Changing rooms - Storage room | - Female changing room + shower - Male changing room + shower - Storage room |
| First Floor | - Social area - Training & meeting room | - Social area - Training & meeting room |
| Second Floor | - Operational zone - Office | - Commander’s office - Operational room |

Design Implications

The Contractor shall:

- develop appropriate structural solutions for the Maritime Police Station, the perimeter wall, the latrines ensuring safety and durability;

- define architectural and finishing works;

- develop a construction timeline;

- Build the facility according to EUCAP purchase orders

- Handing over the facility

Additional interventions shall be limited to those technically necessary to ensure safe execution of the construction scope defined by EUCAP Somalia.

  - Technical proposals

The technical design shall be developed within the scope defined by the EUCAP Somalia.

The Contractor shall:

- verify existing conditions through site inspections, measurements and required investigations;

- define technically justified solution necessary for safe and durable execution of the PMPF activities;

- ensure compliance with applicable legislation and EUCAP technical specifications.

The subsections below define minimum discipline requirements and expected outputs for the Final Design.

The Contractor remains responsible for proposing any additional measures necessary to ensure safety, regulatory compliance and functional integrity of the new building.

    - Structural and Construction

Minimum requirements

- Perform a structural calculation covering load-bearing elements, intermediate floors, connections and roof systems.

- Provide buildable construction details (wall-floor, floor-ceiling, foundations, wet areas, etc).

Outputs

- Structural calculations and drawings (plans/sections/details) for all interventions.

- BoQ and technical specifications for structural works,

- Key construction details,

- Indicative phasing diagram / Gantt overview linked to major work packages,

- Any other supplemental documentation.

    - Material selection

Materials and systems shall be selected to ensure durability, safety, hygiene, maintainability and long-term performance, in full compliance with applicable legislation and minimum national energy performance requirements.

The Contractor shall prioritise cost-effective, market-available and locally serviceable solutions.

Requirement for EUCAP Approval

All proposed material and system selections that affect investment cost, operational performance, maintenance requirements or long-term serviceability shall be submitted to EUCAP for review and written approval prior to finalisation of the technical specifications and Bill of Quantities.

The Contractor shall not finalise material or system choices unilaterally. Where relevant, the Contractor shall propose technically acceptable and economically justified alternatives to support the EUCAP’s decision-making.

Outputs

- Technical specifications and material schedules, clearly identifying items submitted for EUCAP’s approval.

- Bill of Quantities based on EUCAP-approved material and system selections,

- Any other supplemental documentation.

    - Water systems

General Scope

The Contractor shall perform a comprehensive assessment of the existing water supply, wastewater and rainwater systems of the context.

All systems shall comply with applicable local legislation and regulations.

Potable Water System

- Verify connection to the municipal network and assess available pressure and capacity.

- Ensure routing allows maintenance access and avoids leakage risks above sensitive spaces.

Wastewater drainage

- Design and construct a dedicated wastewater system connected to a cesspool, as no centralized sewer network is assumed. The system shall be sized appropriately for a 4-unit toilet block and peak usage.

- Ensure all drainage pipes are laid with adequate slope (minimum 1–2%) to achieve gravity flow and prevent blockages.

- Provide proper ventilation (vent stacks) to avoid odour buildup and ensure system functionality.

- Ensure accessibility for maintenance, including inspection chambers/manholes at appropriate intervals and at all changes in direction.

- Coordinate pipe routing with structural elements, ensuring protection from loads and avoiding interference with foundations.

- Install grease traps (if applicable) and silt traps to limit contamination and sediment entering the septic system.

Rainwater drainage

- Define a functional roof drainage solution appropriate to roof geometry.

- Ensure compliant discharge in line with municipal conditions.

- The site currently does not include a functional perimeter drainage system. The Contractor shall assess the feasibility of introducing appropriate perimeter drainage or equivalent protective measures within the approved scope

Interface requirements

- Coordinate firefighting water supply with Fire Safety discipline.

- Provide dedicated condensate drainage for HVAC systems.

Materials and installation principles

Piping materials and components shall be selected in accordance with national standards, durability requirements and maintenance considerations. Acoustic treatment of drainage systems serving teaching spaces shall be considered, where relevant.

Outputs

- Water supply and drainage layouts,

- Hydraulic calculations (where required),

- Technical specifications,

- Coordinated routing drawings,

- Bill of Quantities,

- Any other supplemental documentation.

    - Electrical systems

General scope

The Contractor shall define the necessary scope for the new systems.

All systems shall comply with applicable national legislation and regulations and technical specifications.

Power supply and distribution

- Verify existing connection capacity and coordinate with the distribution operator where required.

- Define main and sub-distribution arrangements appropriate to building zoning and load requirements.

- Ensure adequate protection measures against electric shock and overcurrent in accordance with national standards.

Lighting

- Provide lighting solutions that meet prescribed illumination levels for administrative buildings.

- Provide emergency and evacuation lighting in accordance with regulations and technical specifications.

- Ensure lighting control solutions appropriate to room function.

Power outlets and equipment supply

The Contractor shall:

- define adequate quantity and distribution of outlets based on functional room layout and intended use;

- ensure appropriate supply for ICT, administrative equipment and technology;

- provide protected and coordinated supply for mechanical, HVAC, hydrotechnical and fire-safety systems.

Earthing and lightning protection

- Include earthing and lightning protection systems.

- Design measures to ensure compliance with applicable standards.

Backup and essential systems

The Contractor shall assess the need for continuity of power supply for critical systems in accordance with applicable regulations and functional requirements (e.g. fire detection, emergency lighting, communication/ICT rooms).

Any proposal shall be subject to the EUCAP’s review and confirmation prior to finalisation.

Coordination requirements

Electrical design shall be fully coordinated with architectural, structural, mechanical, hydrotechnical, ICT and fire-safety disciplines. Routing of cabling and equipment placement shall consider maintenance access and compatibility with structural solutions.

The distribution and positioning of power outlets, data points, lighting fixtures and other electrical components shall reflect the planned furniture layout and equipment requirements (e.g. desks, ICT equipment, projection systems and similar), ensuring safe and practical use of the spaces.

Outputs

- Electrical design drawings (layouts and schematics),

- Single-line diagrams and distribution schemes,

- Lighting calculations (where required),

- Earthing and lightning protection documentation,

- Technical specifications,

- Bill of Quantities,

- Any other supplemental documentation.

    - HVAC

General scope

The Contractor shall define the appropriate scope within the scope and spatial requirements.

All systems shall comply with applicable national legislation and regulations and technical specifications.

Ventilation

Define ventilation solutions in accordance with regulatory requirements and functional needs.

Prioritise technically feasible natural ventilation where possible and introduce mechanical ventilation where required by regulation or justified by occupancy and indoor air quality considerations.

Ensure solutions are acoustically appropriate for administrative environments.

Cooling

Any proposed cooling solution shall be technically and economically justified within the scope of the project.

Noise and vibration

HVAC solutions shall ensure acceptable indoor acoustic conditions in teaching spaces. Equipment mounting, routing and positioning shall minimise vibration and noise transmission.

Coordination requirements

HVAC design shall be coordinated with architectural, structural, electrical, hydrotechnical and fire-safety disciplines.

Outputs

- HVAC layouts and system schematics,

- Equipment schedules,

- Required calculations (ventilation rates, etc.),

- Technical specifications,

- Bill of Quantities,

- Any other supplemental documentation.

    - Firefighting

General scope

Given the building typology and occupant profile, the design shall prioritise life safety, safe evacuation and regulatory compliance.

All systems shall comply with applicable national legislation and regulations and technical specifications.

Fire detection and alarm

- Define the required fire detection and alarm system in accordance with applicable regulations and building use.

- Ensure adequate coverage of all occupied, technical and other spaces.

- Define zoning and notification principles in line with regulatory requirements.

Where required by regulation or competent authority, additional fixed firefighting systems shall be designed accordingly.

Portable firefighting equipment

- Define the type, distribution and quantity of portable fire extinguishers in accordance with fire risk classification and regulations.

- Ensure visible and accessible placement along escape routes and in rooms with increased fire load.

Evacuation and passive fire protection

In coordination with all other sections of technical design, the Contractor shall:

- verify fire compartmentation requirements;

- define escape routes and required fire-rated elements (doors, partitions) where mandated by regulations;

- provide fire safety signage in accordance with national standards;

- coordinate emergency lighting requirements with electrical design.

System integration

Fire safety systems shall be integrated with electrical, HVAC and other relevant systems to ensure appropriate operational response in case of alarm, as required by regulations.

Outputs

- Fire safety regulatory compliance documentation,

- Fire detection and alarm layouts,

- Hydrant system layouts (where applicable),

- Portable extinguisher layout,

- Technical specifications,

- Bill of Quantities,

- Any other supplemental documentation.

    - Others

The Contractor shall define the necessary auxiliary and support systems (including ICT infrastructure, surveillance and other relevant utilities) within the approved framework.

Proposed solutions shall be proportionate to the functional needs of the Police Station.

All systems shall comply with applicable national legislation and relevant technical standards. Proposals shall be subject to EUCAP’s review and confirmation prior to finalisation.

Communications and ICT infrastructure

The Contractor shall define the necessary ICT infrastructure for safe and functional operation of the Police Station.

The design shall include:

- structured cabling solutions for administrative spaces where functionally required;

- provision for wireless network infrastructure in accordance with operational needs;

- coordinated routing of ICT installations within architectural and structural constraints.

All proposed ICT system configurations that materially affect cost, technical complexity or long-term maintenance shall be submitted to EUCAP’s review and written confirmation prior to finalisation.

Sustainability and energy-related considerations

Within the limits of the approved scope, the Contractor shall assess opportunities for improving environmental and energy performance in compliance with applicable national energy efficiency regulations and technical specifications.

This may include:

- energy-efficient lighting and equipment;

- small-scale renewable energy options.

Any proposal exceeding minimum regulatory requirements or materially affecting investment cost shall be subject to EUCAP’s review and confirmation prior to inclusion in the final design.

- Construction of the Facility

- General Objective of assignment

EUCAP Somalia seeks to establish a contract with competent and technically qualified construction firm for the purpose of construction of a Maritime Police station, perimeter Wall and latrine block.

The Contractor shall be contracted to carry out all the construction activities in compliance with international standards as specified in the technical specifications document.

- Expected Milestones and Timelines.

The successful Contractor will perform the following outputs as presented in the table below

| No | Milestone Name and Description of Performance | Time to Complete | % of progress | % of Disbursement |
| --- | --- | --- | --- | --- |
| 01 | Preliminary investigation | 1 month |  |  |
| 02 | Submission of the Final design | 2 month |  | Lumpsum |
| 03 | Building permit (if need it) | 1 month |  | Lumpsum |
| 04 | Completion of Sub-structure and site facilities work | 1 month | 25% | 25% - out of which a corresponding 10% (of the lumpsum) shall be withheld as retention monies |
| 05 | Partial completion of super-structure and water facilities | 2 months | 40% |  |
| 06 | All the work of super-structure completed with finishing | 1 month | 80% |  |
| 07 | All the Civil, Plumbing, Electrical, IT land levelling work completed. | 1 month | 90% |  |
| 08 | Final statement of accounts | 1 month | 100% | 75% - out of which a corresponding 10% (of the lumpsum) shall be withheld as retention monies |
| 09 | Perimeter boundary wall erected, painted, completed as per BoQ. (if applicable) | 3months | 100% | 100% - out of which a corresponding 10% (of the lumpsum) shall be withheld as retention monies |

- Site Management Guideline for the Contractor(s)

The entire operation of the construction works shall be superintended by a Team Leader (Engineer) from contractor(s) side.

The incumbent shall maintain a close contact with the designated officer of EUCAP on site to coordinate the performance of the overall construction project.

Team Leader shall be responsible for following but not limited to:

- Ensuring entire construction work following standards and compliances as specified

- Health checking of workers, workers information every day before staring of the work and reporting to EUCAP

- Manage the overall work schedule as proposed in the bidding and agreed with EUCAP

- Manage the micro work schedule during implementation period as per the guidance and instruction from EUCAP.

- Document and report on progress of works on a daily/weekly/monthly basis to the authorized officer of EUCAP

- Participating weekly progress review meeting with EUCAP

- Monitor / manage corrective and preventive services on site

- Monitor/Inspect activities and personnel on site

- Implement controls determined in the site management Plan

- Ensuring environmental issues are addressed and mitigated

- Overall construction management from starting to handover of the project

- Facilitate the EUCAPs technical Committee visits bi-weekly / monthly to site

- Quality Control

The Contractor shall institute an appropriate inspection system including control tables of duties to ensure the predetermined duties are carried out by the staff.

Any shortcomings and/or substandard conditions noted in such inspections shall be promptly corrected and improved; any conditions beyond the responsibility of the Contractor shall be brought to the attention of EUCAP’s representative on site for disposition.

The selected bidder must provide a quality control plan, materials handling plan, records keeping, detailed work plan, solid waste management plan, water conservation plan, occupational health and safety plan, environmental management plan. These plans will be closely monitored during execution. The successful bidder must submit the quality control plan for review and approval before the commencement of works.

- Security of Staffs and construction materials:

The Contractor shall be responsible to carry out a security check on all staff to be employed for these works and ensuring security of construction materials carried to the site. Contractor shall not allow any staff without safety kits on site, and risky areas shall clearly be marked. During the night contractor is responsible to ensure lights on construction site and maintain security on site 24/7.

- Duration of contract

The Construction work shall be completed within 9 (nine) months starting from the issuance of the Contract. The contractor must ensure the execution in 9 months keeping in view the design, specifications, market, weather conditions and all other risks associated with construction that may delay the project in the context of Puntland, Somalia.

- Test Result of construction materials

Report and/or laboratory report as guided by acceptable international and/or national building code is accepted by the EUCAP PM and/or authorized technical officer.

Failing to do so will automatically reject the construction materials supplied by the contractor. On the construction site must be tested as per the international standard or national building code prior to use and test report must be submitted to EUCAP PM and/or authorized officer.

The materials can be used on the site only when the report is accepted by EUCAP. In case of NTI (not tie in) works EUCAP shall not be responsible to compensate or consider any work which is done without prior approval of EUCAP.

- Lump Sum Contract Price and Milestone Payments

The Bill of Quantities (BoQ) is an itemized breakdown of the works to be carried out, indicating a quantity for each item and the contractor are required to provide the corresponding unit prices.

During the construction, each line item will be re-measured on a regular basis and payment amount shall be determined by applying the unit rates to the quantities executed for the respective items.

Payment will be made on completion of set milestones, and the unit rates/prices for each element are not subject to adjustment or revision because of price or currency fluctuations, or the actual costs incurred by the Contractor in the performance of the Contract. Only the quantities may go up or down.

The Contractor shall Request for Inspection (RFI) upon completion of each milestone and the milestone must be certified by the authorized officer of EUCAP.

Based on the certification, the contractor is responsible for submitting invoice as per set milestone. During invoice submission, the contractor must submit all the test reports.

Failing to do so, payment will not be processed, and EUCAP will not be responsible for the delay of such payments.

- Schedule of Payments

Payments will be made to the contractor upon completion of each Milestone as indicated in Section above.

N.B: After the substantial completion of the work, the completed work will be monitored by EUCAP for 12 months from the date of substantial completion. If there is any defect discovered, the construction company shall be liable to do the necessary rectifications of works as per the direction and guidance of EUCAP.

- See attached the following Annex

SD1_Bosaso-Floor Plan & Section Drawings

SD2_Septic tank

SD3_Fencing Wall Design_PMPF

SD4_Toilet Block

SD5_Police station Rendering

SD6_MARITIME POLICE STRUCTURAL DETAILS

SD7_Bossaso Police Station Electric Plan

SD8_LOAD SCHEDULE BALANCEMENT

SD9_EUCAP_Technical specifications